## Sheet1
| TASKS |  | Timeline | Assigned To | Comments/Notes
| Vendor Selection |  | RFP Drafts Finalized: 10/31/2014 |  | Timeline is based on the assumption that new RFP's will need to be developed, and will support a seamless transition from pilot to product so as to not negatively impact the services that are in production
|  | Cloud Vendor | RFP's Released (45 day response period): 11/01/2014 - 12/15/2015
|  | Help Desk Support | Vendor Selection (45 Day Review Period; includes Legal components): 12/15/2014 - 1/31/2015
|  | Operations Support | Transition: 2/1/2015 - 6/30/2015
Dataflux (matching and address validation)
Business Model & Funding Plan
3 |  | Cost to participants |  | I2 & PESC ? | Should this also be kicked off by the principles?
3 |  | Expecation of participants
| Governance |  |  |  | Product governance document being worked on by the principles.
1 |  | Product Governance |  | I2 & PESC
2 |  | Daily Operations Decisions | handling duplicate accounts, - will need to review all of our current procedures and ensure that responsibility for each of the tasks are assigned to vendors | Projcet Teams
2 |  |  | list out all of the volunteer resources and what they are doing, (jimmy, Stewart) | Projcet Teams
3 | Branding |  | leverage students from the pilot to get their reaction to the branding, or to suggest branding,
5 | Strategic Planning |  | outreach to AACRAO, NACAC etc validation of the service;
5 | Communication Plan
5 | Marketing | Plan | bringing on new partners, service providers,
| Product Enhancements |  |  |  | Do we need to try and re-engage additional community participation in these discussions? How can we effectively do that?
2 |  | Technical |  | Tech Team?
2 |  | Business/UI |  | Business Team?
this will also help with the marketing and communication planning;
|  | External security review | higher security credentials can be provided to campuses

## Sheet2
| TASKS |  | Timeline | Assigned To | Comments/Notes
1 | Governance | Product Governance | In Process - Shel to draft and work with MDS on the structure. | I2 & PESC | Product governance document being worked on by the principles.
2 | Governance | Daily Operations Decisions | Launch Call set for 18 September | Product Team
2 | Product Development | Volunteer Resources | Discussion will commence once current development work has been finalized - Should be completed mid-late September | Pilot Team
2 | Product Development | Contracted Resources | handling duplicate accounts, - will need to review all of our current procedures and ensure that responsibility for each of the tasks are assigned to vendors | Product Team
2 | Product Enhancements | Technical | Launch Call set for 18 September - Goal to complete by mid October | Product Team
2 | Product Enhancements | Business/UI | Launch Call set for 18 September - Goal to complete by mid October | Product Team | Need to re-engage community participants
2 | Vendor Selection | External security review | Need to finalize infrastructure first - target date: Can utilize I2 and Pilot Participant resources. Serrvice Validation checklist from net+ (Ann will assist) | Pilot Team | higher security credentials can be provided to campuses; Work with Pilot team to review outstanding tickets, and identify if additional infrastructure changes will need to be made for the Pilot
3 | Business Model & Funding Plan | Cost to participants |  | I2 & PESC | I2 and PESC will work on this along with the Governance document
3 | Implementation & Deployment | Expecation of participants |  | Pilot Team | What resources are required for implementation? How do you get started? Need it from a functional and technical perspective. One pager for exec.
3 | Branding |  |  | I2 & PESC | I2 and PESC will work on this along with the Governance document
4 | Vendor Selection | Cloud Vendor | RFP Drafts Finalized: 10/31/2014; RFP's Released (45 day response period): 11/01/2014 - 12/15/2015; Vendor Selection (45 Day Review Period; includes Legal components): 12/15/2014 - 1/31/2015; Transition: 2/1/2015 - 6/30/2015 |  | Timeline is based on the assumption that new RFP's will need to be developed, and will support a seamless transition from pilot to product so as to not negatively impact the services that are in production
4 | Vendor Selection | Help Desk Support | TBD based on experience from USC Pilot |  | This will need to be delayed until we have experience with the USC pilot to fully flesh out what Help Desk service requirements will need to be for the Product
4 | Vendor Selection | Operations Support | RFP Drafts Finalized: 10/31/2014; RFP's Released (45 day response period): 11/01/2014 - 12/15/2015; Vendor Selection (45 Day Review Period; includes Legal components): 12/15/2014 - 1/31/2015; Transition: 2/1/2015 - 6/30/2015 |  | Timeline is based on the assumption that new RFP's will need to be developed, and will support a seamless transition from pilot to product so as to not negatively impact the services that are in production
4 | Vendor Selection | Dataflux (matching and address validation) | RFP Drafts Finalized: 10/31/2014; RFP's Released (45 day response period): 11/01/2014 - 12/15/2015; Vendor Selection (45 Day Review Period; includes Legal components): 12/15/2014 - 1/31/2015; Transition: 2/1/2015 - 6/30/2015 |  | Timeline is based on the assumption that new RFP's will need to be developed, and will support a seamless transition from pilot to product so as to not negatively impact the services that are in production
4 | Legal Framework | Participation Agreements |  |  | Look at InCommon agreements to identify the content of this document
4 | Legal Framework | Privacy and Terms of Use - End User
4 | Legal Framework | Privacy and Terms of Use - Participants & Service Providers
4 | Legal Framework | Terms and Conditions for Participants & Service Providers |  |  | Look at InCommon agreements
5 | Strategic Planning |  | leverage students from the pilot to get their reaction to the branding, or to suggest branding,
5 | Communication Plan
5 | Marketing | Marketing & Outreach Planning |  |  | outreach to AACRAO, NACAC etc validation of the service; bringing on new partners, service providers,